|  | Order 890 Work Plan |  |  |  |
| --- | --- | --- | --- | --- |
| Order Cite | Action Item/Work Plan | Action Item Home | Target Dates | Status |
| ATC GROUP ASSIGNMENTS (ESS/ITS and BPS) |  |  |  |  |
| 243, 246 | - Business Practice Standards complementary to NERC Reliability Standards for Existing Transfer Capability (ETC) to create a “consistent approach for determining the amount of transfer capability a transmission provider may set aside for its native load and other committed uses”, including the elements of ETC for full implementation of the NERC MOD-001 reliability standard | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 257, 262 | - Capacity Benefit Margin (CBM) Business Practices - Business practice standards to set forth “how the CBM value shall be determined, allocated across transmission paths, and used” and how transmission providers will “reflect the set-aside of transfer capability as CBM in the development of the rate for point-to-point transmission service.” - Business practice standards that include an OASIS mechanism to “allow for auditing of CBM usage.” - Any additional business practice standards needed to complement the NERC CBM reliability standards created as a result of this effort | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 272, 273 | - Transmission Reliability Margin (TRM) Business Practice Standards to complement the NERC reliability standards for TRM - The business practice standards will include specification of the appropriate uses of TRM and when transmission providers may set aside TRM | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 293 | - Business practice standards for accounting for counterflows. These standards will be included in the ATC business practice standards. | WEQ Annual Plan Item 2 |  |  |
| 301, 310, 369 | - Business practice standards to address the frequency and posting requirements for all ATC components that are complementary to the related NERC reliability standards: - Business practice standards for data exchange for ATC modeling complementary to the related NERC reliability standards including any OASIS posting requirements to achieve the data exchange - Business practice standards that will set forth how transmission providers will post “explanations of the reason for a change in monthly and yearly ATC values on a constrained path.” The standards will include a requirement that that the transmission provider post the reason for the change in a narrative form. The posted information will include “the (1) specific events which gave rise to the change and (2) new values for ATC on that path (as opposed to all points on the network).” - *See ESS/ITS Assignments GROUP 4 for development of OASIS business practices related to ATC and all ATC components posting requirements. The ATC Group should develop standards related to the NERC reliability standards and the ESS/ITS should develop posting requirements/revisions to S&CPs to implement the ATC Group’s standards. | WEQ 2007 Annual Plan Item 2 and Request No. R05004A | FORMAL COMMENT: The ESS/ITS and BPS plan to post a recommendation that includes NAESB Business Practices for frequency and posting requirements for all ATC components for formal comment on June 1, 2007 WEQ EC VOTE: RATIFICATION: |  |
| 246, 413 | Business Practice Standards for ATC and AFC Calculation Methodologies to complement the NERC reliability standards created for ATC and AFC Methodologies (NERC MOD001; NERC MOD028; NERC MOD029; and NERC MOD030) - Business practice standards for posting on OASIS of the “underlying load forecast assumptions for all ATC calculations” - Business practice standards for posting on OASIS of the “actual daily peak load for the prior day.” | WEQ 2007 Annual Plan Item 2 and Request No. R05004A | FORMAL COMMENT: The ESS/ITS and BPS plan to post a recommendation that includes Business Practices for any other requirements that come out of NERC’s revision to MOD001 for formal comment on July 1, 2007 WEQ EC VOTE: RATIFICATION: |  |
|  | - Business practice standards to complement NERC reliability standards for Transfer Capability | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
|  | - Business practice standards to set forth the procedure for input on TTC and ATC methodologies and values - During the Order 890 NERC and NAESB joint standards development effort, it was determined that the standards contained in MOD003 should be business practice standards instead of reliability standards. NERC has requested that NAESB adopt the standards as business practices via correspondence to Ms. McQuade, NAESB President. | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |

|  | Order 890 Work Plan |  |  |  |
| --- | --- | --- | --- | --- |
| Order Cite | Action Item/Work Plan | Action Item Home | Target Dates | Status |
| ESS/ITS ASSIGNMENTS |  |  |  |  |
| 815 | GROUP 0: RESALES |  |  |  |
|  | - The OASIS business practices developed to align the existing NAESB standards with Order 890 will include the requirement that “all sales or assignments of capacity be conducted or otherwise posted on the transmission provider’s OASIS on or before the date the reassigned service commences.” | WEQ 2007 Annual Plan Item 2 | FORMAL COMMENT: The ESS/ITS plans to post a recommendation for formal comment that includes revisions to the Resales standards to address the directives in Order 890 after the April 3-4 meeting in time for the WEQ EC to vote on the recommendation at the May 8 meeting. WEQ EC VOTE: The WEQ Executive Committee adopted a revised recommendation during the May 8 WEQ EC meeting. RATIFICATION: | The Recommendation for the business practices was posted for formal comment on April 5, 2007 with comments due on May 4. The WEQ Executive Committee is scheduled to vote on this Recommendation at its May 8, 2007 meeting in Washington, DC. The modifications to the S&CPs will be processed under a separate recommendation that will also include other changes to the S&CPs required in Order 890. |
|  | GROUP 1: METRICS; RE-BID OF PARTIAL SERVICE; PRECONFIRMATION OF PRIORITY; REDISPATCH COST POSTING* |  |  |  |
| 413 | - Metrics: Business Practice standards s to “post on OASIS metrics related to the provision of transmission service under the OATT” including the posting of: - “the number of affiliate versus non-affiliate requests for transmission service that have been rejected”; - “the number for affiliate versus non-affiliate requests for transmission service that have been made”; - These standards will also set forth in the above referenced posting requirements the length of the service request and the type of the service requested | WEQ 2007 Annual Plan Item 2 | FORMAL COMMENT: The ESS/ITS plans to post a recommendation for the ESS/ITS Group 1 items for formal comment with comments due by the end of 2nd Quarter 2007 WEQ EC VOTE: RATIFICATION: |  |
| 1318 | - Metrics: OASIS business practice standards to implement the standard performance metrics set forth in Order 890, Paragraphs 1308-1317. |  | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 1005, 1162 | Redispatch Cost Posting: Business practices for redispatch cost postings: - The business practice standards for redispatch cost postings will include OASIS business practices and any needed additions or revisions to the OASIS Standards & Communication Protocols (S&CPs) to allow for posting of third party offers of planning redispatch services. The business practice standards developed for redispatch cost postings may affect the existing NAESB business practice standards for Transmission Loading Relief. - The posting of redispatch information will also include the posting of each transmission provider’s “monthly average cost of redispatch for each internal congested transmission facility or interface over which it provides redispatch service using planning redispatch or reliability redispatch under the pro forma OATT.” - The business practice standards for redispatch cost postings will also include functionality for transmission providers to post “a high and low redispatch for the month” each internal congested transmission facility or interface over which it provides redispatch service |  | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 1378 | Re-bid of Partial Service: OASIS Business practice standards and OASIS S&CPs for re-bid of partial service - NAESB will develop business practice standards to “allow a transmission customer to rebid a counteroffer of partial service so the transmission customer is allowed to take the same quantity of service across all linked transmission service requests. |  | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 1392 | - Pre-confirmation of Priority: Development of OASIS business practice standards and OASIS S&CPs to prohibit “transmission customers from changing a request into a pre-confirmed request and requiring OASIS platforms to be accessible on non-Windows/Explorer computers |  | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
|  | GROUP 2: NETWORK SERVICE ON OASIS |  |  |  |
| 385 | - Development of OASIS business practice standards and OASIS S&CPs for “transmission providers and network customers to use OASIS to request designation of new network resources and to terminate designation of network resources.” The standards will include the ability to query requests to designate and terminate network resources and will require development of OASIS templates. - Shall be posted on OASIS for 90 days and available for audit for a 5 year period Will result in ability of Transmission customers to be able to query requests to designate and terminate a network resource. Requests and responses made electronically. | WEQ 2007 Annual Plan Item 2 and Request No. R04006E | FORMAL COMMENT: The ESS/ITS plans to post a recommendation for ESS/ITS Group 2 items for formal comment with comments due by the end of 3rd Quarter 2007 WEQ EC VOTE: RATIFICATION: |  |
| 1477 | - Development of OASIS business practice standards and OASIS S&CPs for provision of the designation of network resources electronically; masking of information “about operating restrictions and generating cost on OASIS”; and to “allow for queries of all information provided with designation requests | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 1477 | - Development of OASIS business practice standards and OASIS S&CPs that describe “the procedural requirements for submitting designations over any new OASIS functionality. | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 1504 | - Development of OASIS business practice standards and OASIS S&CPs to specify how designated network service informational postings are posted on OASIS . - Develop details of how the view, download, and query requirements for information posted regarding network resource designations informational postings. | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 1532 | - Development of OASIS business practice standards and OASIS S&CPs to set forth the “treatment of OASIS requests when the customer fails to provide the necessary attestation,” when submitting a request to designate a new network resource. - Attestation: Formatting of attestation information that will be provided on OASIS. | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 1541 | - Development of OASIS business practice standards and OASIS S&CPs to describe “the procedural requirements for submitting both temporary and indefinite terminations of network resources, to allow network customers to provide all required information for such terminations.” These business practice standards will include the functionality set forth in Order 890, Paragraph 1541. | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 1541 | - Development of OASIS business practice standards and OASIS S&CPs to describe “the procedures for submitting and processing requests for concomitant evaluations of transmission requests and temporary terminations. | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
|  | GROUP 3: CONDITIONAL FIRM; PRE-EMPTION; REQUEST R05019; and REVISIONS TO STANDARD 9.7 |  |  |  |
| 1078 | Conditional Firm: In Paragraph 1078 of Order 890, the Commission directed transmission providers to “assign short-term firm service to conditional firm customers as the service becomes available.” The Commission also directed transmission providers to work with NAESB to “develop the appropriate communications protocols to implement this attribute of conditional firm service.” NAESB will develop OASIS business practices and OASIS S&CPs that will implement the ability to assign short-term firm service to conditional firm customers. Development of communication protocols for conditional firm including tracking mechanism and regional variation. Need to review the tagging rules related to the use of conditional firm. | WEQ Annual Plan Item 2 | FORMAL COMMENT: The ESS/ITS plans to post a recommendation for ESS/ITS Group 3 items for formal comment with comments due by the end of 4th Quarter 2007 WEQ EC VOTE: RATIFICATION: |  |
| 1269 | Revisions to Standard 001-9.7: NAESB will continue to work to revise NAESB WEQ business practice standard WEQ 001-9.7 (which addresses rollover rights for Redirected transmission service) to be consistent with the Commission’s policies. | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 1407 | Pre-emption: Revise OASIS business practice standards and OASIS S&CPs so that “a new pre-confirmed request for transmission service would preempt a request of equal duration that has been accepted by the transmission provider but not yet confirmed by the transmission customer.” It is the expectation that the business practice standards to address preemption will be developed in conjunction with NAESB Request No. R05019 to modify OASIS standards and OASIS S&CPs to clearly document the procedures used to implement the displacement/interruption terms of the Pro Forma tariff. This is consistent with NAESB Standard WEQ 001-4.25. | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
|  | GROUP 4: ATC RELATED POSTINGS and COUNTERFLOWS** |  |  |  |
|  | ATC Related Postings | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
|  | The plan for addressing the Group 4 items can be found in the ATC related items section of the work plan above. |  |  |  |
| 1377 | GROUP 5: PARAGRAPH 1377*** |  |  |  |
|  | NAESB will develop business practice standards to facilitate the coordination of requests across multiple transmission systems using the principles set forth in Paragraph 1377 of Order 890. Develop S&CPs related to coordination of request across multiple transmission systems. | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
|  | GROUP 6: MISCELLANEOUS |  |  |  |
| 1390 | NAESB plans to review the existing business functions set forth in the NAESB WEQ standards to determine if changes should be made to address Paragraph 1390 of Order 890. FERC: OATT is sufficient to allow a Transmission Provider to manage situations where the Transmission Customer modifies its application for service to the point that the request is “meaningfully different” than initial request. ESS/ITS: need to review if this has any impact on business functions. | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |
| 1627 | Development of OASIS business practice standards and OASIS S&CPs for “the posting of additional curtailment information on OASIS” via a “detailed template for the posting of additional information on OASIS regarding firm transmission curtailments. Posting of curtailment information on OASIS: develop a detailed template for the posting of additional information on OASIS regarding firm transmission curtailments. | WEQ Annual Plan Item 2 | FORMAL COMMENT: WEQ EC VOTE: RATIFICATION: |  |