| NORTH AMERICAN ENERGY STANDARDS BOARD 2006 ANNUAL PLAN for the RETAIL GAS and ELECTRIC QUADRANTS Revisions Proposed by the Retail Gas and Electric Quadrants on August 16, 2006 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Item Number & Description |  |  | Completion | Assignment |
| 1 |  | Billing & Payment |  |  |  |  |
|  |  | a. | Develop Technical Electronic Implementation Standards – Billing & Payments Status: Underway |  | 3rd Qtr. 2006 | TEIS |
|  |  | b. | Develop additional model business practices for reversal and reissue, transformer loss factors, budget billing and payment plans, and missed bill windows Status: Completed through the BPS process and submitted to IR. |  | 4th Qtr 2006 | IR |
| 2 |  | Pre-Enrollment Customer Information |  |  |  |  |
|  |  | a. | Develop technical transaction processes for exchanging customer information necessary for interactions prior to enrollment and billing, i.e., customer authorization procedures, identifying types of customer information necessary for pre-enrollment activities, and methodologies for exchanging information. Status: Underway. To be presented at the November EC meeting. |  | 3rd Qtr. 2006 | TEIS |
| 3 |  | Electronic Retail Billing. |  |  |  |  |
|  |  | a. | Develop information requirements for electronic retail billing transactions and bill payment transactions between customers, suppliers, and utilities pursuant to Request No. R05016. Status: Completed. |  | 1st Qtr. 2006 | IR |
|  |  | b. | Develop Technical Electronic Implementation Standards – Electronic Retail Billing Status: Underway. To be presented at the November EC meeting. |  | 3rd Qtr. 2006 | TEIS |
| 4 | Customer Enrollment, Drop and Account Maintenance |  |  |  |  |  |
|  | a. |  | Develop practices for submitting and receiving, processing and fulfilling a customer’s request to enroll with or leave a supplier (including suppliers dropping customers) and for maintaining current customer account information, and for notifying affected parties. Status: Underway. To be presented at the November EC meeting for enrollment part. |  | 2nd Qtr. 2007 | BPS |
|  | b. |  | Develop information requirements for submitting and receiving, processing and fulfilling a customer’s request to enroll with or leave a supplier (including suppliers dropping customers) and for maintaining current customer account information, and for notifying affected parties. Status: Not Started. Customer enrollment should be complete by 4th Qtr 2006, but drops and customer account information should span into 2007. |  | 3rd Qtr. 2007 | IR |
|  | c. |  | Develop Technical Electronic Implementation Standards – Customer Enrollment, Switching & Dropping. Status: Not Started |  | 4th Qtr 2007 | TEIS |
| 5 | Customer Inquiries |  |  |  |  |  |
|  | a. |  | Develop procedures for responding to customer inquiries directed to Distributors and/or Suppliers and for notification of the other party. Status: Not Started |  | 4th Qtr. 2007 | BPS |
| 6 | Contracts |  |  |  |  |  |
|  | a. |  | Develop a model RGQ/REQ contract/outline modeled after the NAESB Base Contract for Sale and Purchase of Natural Gas, NAESB Standard 6.3.1 (NAESB Base Contract for Gas) designated for use by electric power markets or competitive gas markets. (R05013). Status: Underway. To be presented at the November EC meeting. |  | 4th Qtr. 2006 | Contracts |
| 7 | Prepare a joint analysis with the WGQ for AS2 and AS3 protocols as compared to the NAESB IET. Status: Not Started. |  |  |  | 4th Qtr. 2006 | TEIS & WGQ EDM |
| 8 | Develop NAESB Certification checklist criteria for Retail Quadrants to be used in the NAESB Certification Program. Status: Not Started. |  |  |  | 4th Qtr. 2006 | TEIS |
| 9 | Partner with the Department of Energy’s Sandia National Laboratories on NAESB technical standards and respond to the surety assessment findings and recommendations. Status: Underway |  |  |  | 4th Qtr. 2006 | EC Officers |
| Program of Standards Maintenance & Fully Staffed Standards Work |  |  |  |  |  |  |
|  |  | Business Practice Requests |  |  | Ongoing | Assigned by the EC |
|  |  | Information Requirements and Technical Mapping of Business Practices |  |  | Ongoing | Assigned by the EC5 |
|  |  | Ongoing Interpretations for Clarifying Language Ambiguities |  |  | Ongoing | Assigned by the EC5 |
|  |  | Ongoing Maintenance of Code Values and Other Technical Matters |  |  | Ongoing | Assigned by the EC5 |
|  |  | Ongoing Development and Maintenance of Definitions |  |  | Ongoing | Glossary |
| Provisional Activities |  |  |  |  |  |  |
|  |  | Review security standards as may be deemed necessary, such as Public Key Infrastructure (PKI). |  |  |  |  |
| Future Activities |  |  |  |  |  |  |
|  |  | Joint Effort: |  |  |  |  |
|  |  |  |  | Supplier Certification: Develop practices for Distribution Companies to register/certify new Suppliers when they seek to begin doing business in the Distribution Company’s service area. |  |  |
|  |  |  |  | Modify TPA as necessary. |  |  |
|  |  | Retail Electric Quadrant Effort Only: |  |  |  |  |
|  |  |  |  | Retail Meter Data Validation, Editing & Estimating: Develop procedures for insuring the integrity and validity of retail customer metering data that is needed by utilities and suppliers for billing, etc. Issues related to unbundled or competitive metering are not to be considered. |  |  |
|  |  |  |  | Load Profiling: Develop practices for using statistical methods to estimate interval consumption by customers who do not have interval meters. |  |  |
|  |  |  |  | Settlement Process: Reconcile energy schedules and energy delivered by suppliers within a given market. Note: will need to be coordinated with the WEQ. |  |  |
|  |  | Retail Gas Quadrant Effort Only: |  |  |  |  |
|  |  |  |  | Examine Wholesale Gas Quadrant Non-EDM Standards for applicability to retail business practices. |  |  |

Retail Electric & Retail Gas

Quadrant Executive Committees

(REQ and RGQ ECs)

Business Practices

Subcommittee (BPS)

Contracts Subcommittee

Glossary Subcommittee

Information Requirements

Subcommittee (IR)

Technical Electronic

Implementation Subcommittee

(TEIS)

Model Business

Practice

Development

Task Forces & Working Groups6

Technical

Standards

Development

NAESB RGQ EC and Subcommittee Leadership:

Executive Committee:  Mike Novak, Chair and Suzanne Calcagno, Vice-Chair

Business Practices Subcommittee:  Phil Precht

Information Requirements Subcommittee:  George Behr

Technical Electronic Implementation Subcommittee:  George Behr

Contracts Subcommittee:  Marcy McCain and Suzanne Calcagno

Glossary Subcommittee:  Don Sytsma

NAESB REQ EC and Subcommittee Leadership:

Executive Committee:  Ruth Kiselewich, Chair and Ed Overtree, Vice-Chair

Business Practices Subcommittee:  Mary Edwards and Dan Jones

Information Requirements Subcommittee:  Ed Overtree

Technical Electronic Implementation Subcommittee:  Jennifer Teel

Contracts Subcommittee:  Ed Overtree

Glossary Subcommittee:  Mary Edwards and Patrick Eynon

End Notes:

? As outlined in the NAESB Bylaws, the REQ and RGQ will also address requests submitted by members and assigned to the REQ and RGQ through the Triage Process.

Dates in the completion column are by end of the quarter for completion by the assigned committee.  The dates do not necessarily mean that the standards are fully staffed so as to be implementable by the industry, and/or ratified by membership.  If one item is completed earlier than planned, another item can begin earlier and possibly complete earlier than planned.  There are no begin dates on the plan.

The project with SNL is a four quadrant effort, with all EC officers providing support to the SNL representatives.

This work is considered routine maintenance and thus the items are not separately numbered.

The REQ and RGQ ECs will assign maintenance efforts on a request by request basis.

6 The ECs and the subcommittees can create task forces and working groups to support their development activities for development of model business practices and technical standards.