## Open Items
BPS/ESS/ITS Action Items
Issue # | Item Number | Status | Description | Assigned to | Dates |  |  | Notes
|  | O = Open |  |  |  |  | Meeting
| (Request Number or | C = Closed |  |  |  |  | When will
| Annual Plan Number) | H = On Hold |  |  | Assigned | Due | be Addressed
35 |  | C | Approve BPS/ESS/ITS 01/03/2008 and 01/04/2008 meeting minutes | Subcommittee |  | 2008-05-14 |  | 5/14/2008 - Meeting Minutes were approved by the Joint Subcommittee.
36 |  | O | Post Final BPS/ESS/ITS 01/03/2008 and 01/04/2008 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 35.
57 |  | O | Draft Standards for OASIS Mechanism to Audit CBM Usage | JT Wood
58 |  | O | Post document provided by JT Wood (draft standards for OASIS mechanism to audit CBM usage) | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 57.
59 |  | O | Draft Request for Standards for OASIS Mechanism to Audit CBM Usage | JT Wood
60 |  | O | Post document provided by JT Wood (draft request for standards for OASIS mechanism to audit CBM usage) | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 59.
78 |  | H | Using the List of ATC Information, begin addressing which items should be confidential based on commercial concerns | Subcommittee |  |  |  | 5/13/2008 On Hold pending direction from the EC.
80 |  | O | Approve BPS/ESS/ITS 01/16-17/2008 meeting minutes | Subcommittee | 2008-01-17
81 |  | O | Post Final BPS/ESS/ITS 01/16-17/2008 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 80.
85 |  | O | Approve BPS/ESS/ITS 01/28/2008 meeting minutes | Subcommittee | 2008-01-28
86 |  | O | Post Final BPS/ESS/ITS 01/28/2008 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 85.
93 |  | C | Approve BPS/ESS/ITS 01/11/2008 meeting minutes | Subcommittee | 2008-01-11 |  |  | 5/14/2008 - Meeting Minutes were approved by the Joint Subcommittee.
94 |  | O | Post Final BPS/ESS/ITS 01/11/2008 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 93.
95 |  | O | Publish and Post NERC/NAESB AFC/ATC Joint Call Draft Minutes from 2/8/2008 | NAESB Staff | 2008-02-08
99 |  | O | Approve BPS/ESS/ITS 02/13/2008 meeting minutes | Subcommittee | 2008-01-28
100 |  | O | Post Final BPS/ESS/ITS 02/13/2008 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 99.
103 |  | O | Approve BPS/ESS/ITS 02/21-22/2008 meeting minutes | Subcommittee | 2008-02-22
104 |  | O | Post Final BPS/ESS/ITS 02/21-22/2008 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 101.
126 |  | C | Talk to leadership team about working on ATC Information List | Ed Skiba | 2008-03-13 |  | 2008-05-13 | Will be inlcuded in Update to EC on May 13th. 5/13/2008 - EC created a task force to provide guidance on what the Joint Subcommittee should do with the ATC Information List.
140 |  | O | Approve Joint NERC/NAESB 4/7/2008 meeting minutes | Subcommittee
141 |  | O | Post Final Joint NERC/NAESB 4/7/2008 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 140.
142 |  | O | Approve BPS/ESS/ITS 04/07/2008 meeting minutes | Subcommittee
143 |  | O | Post Final BPS/ESS/ITS 04/07/2008 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 142.
145 |  | O | Review NERC MODs once finalized to confirm that ATC postings at a minimum are consistent with the NERC recalculations. | Co-Chairs NAESB Staff | 2008-04-16 |  |  | Documents need to be reviewed after the NERC Mods have been finalized.
151 |  | O | Approve Joint BPS/ESS/ITS 4/16-17/2008 meeting minutes | Subcommittee | 2008-04-17
152 |  | O | Post Final Joint Joint BPS/ESS/ITS 4/16-17/2008 meeting minutes | NAESB Staff | 2008-04-17 |  |  | Action item is dependent on the completion of Action Item 151.
158 |  | C | Update ATC Information List to reflect current MOD standards (data and requirements cross reference) | Barry Green | 2008-05-01 | 2008-05-09 | 2008-05-14 | List was updated and sent to NAESB for posting on May 9th
159 |  | C | Develop and Post Agenda for May 14-16 ESS/ITS & BPS Meeting | Co-Chairs NAESB Staff | 2008-05-01 | 2008-05-07 |  | Agenda was sent to NAESB on May 5th. Agenda was posted on May 12th.
160 |  | C | Create draft presentation for EC Meeting and distribute to group | Ed Skiba | 2008-05-01 | 2008-05-06 |  | Presentation was sent to the BPS/ESS/ITS Exploder list on 5/6/2008.
161 |  | C | Follow-up with Rae McQuade on options available for making ATC Information List Available without including it in the Business Practices Book as a Standard. | Jonathan Booe | 2008-05-01 | 2008-05-14 | 2008-05-14 | This is no longer a BPS/ESS/ITS issue. The Exec Comm has set up a task force to provide guidance to the Joint Subcommittee on what to do with the ATC Information List.
162 |  | C | Check with NERC ATCDT to determine if NAESB can add information into the ATCID | Ed Skiba | 2008-05-14 |  | 2008-05-15 | Andy Rodriquez and ATCDT co-chairs indicated they would not have issues with NAESB including information into ATCID.
163 |  | C | Send NERC ATCDT copy of Counterflow/Postback recommendation and request NERC team review document prior to May 29th joint meeting | Ed Skiba | 2008-05-15 | 2008-05-15 |  | Document was sent to Andy Rodriquez and ATCDT co-chairs with request that the NERC team provide comments at the May 29th meeting.
164 |  | C | Notify NAESB and EC Chair/Co-Chair that Joint BPS and ESS/ITS will take responsibilty for ETC Posting annual plan item 2.a.vi.4 | Ed Skiba | 2008-05-15 | 2008-05-15 |  | Email was sent on May 15th.
165 |  | O | Approve Joint BPS/ESS/ITS 5/14-16/2008 meeting minutes | Subcommittee | 2008-05-16
166 |  | O | Post Final Joint Joint BPS/ESS/ITS 5/14-16/2008 meeting minutes | NAESB Staff | 2008-05-16 |  |  | Action item is dependent on the completion of Action Item 165.
167 |  | C | Send email to exploder list requesting joint subcommittee review questions and issues for ETC components (Grandfathered Commitments and Rollover Rights) | Ed Skiba | 2008-05-16 | 2008-05-16 | 2008-05-29 | Email sent on 5/16/2008
168 |  | C | Notify NAESB Staff to revise meeting calendar to indicate May 28th date will be given to ESS/ITS to work on Conditional Firm | Ed Skiba | 2008-05-16 | 2008-05-17
169 |  | O | Develop and Post Agenda for May 29th ESS/ITS & BPS Meeting | Ed Skiba NAESB Staff | 2008-05-16 | 2009-05-20
170 |  | O | Develop and Post Agenda for May 29th Joint NERC/NAESB Conference Call | Ed Skiba NAESB Staff | 2008-05-16 | 2009-05-20
171 |  |  | Next number to be assigned

## Closed Items
BPS/ESS/ITS Action Items
Issue # | Item Number | Status | Description | Assigned to | Dates |  |  | Notes
|  | O = Open |  |  |  |  | Meeting
| (Request Number or | C = Closed |  |  |  |  | When will
| Annual Plan Number) | H = On Hold |  |  | Assigned | Due | be Addressed
1 |  | C | Approve BPS/ESS/ITS 05/03/2007 meeting minutes | Subcommittee |  |  | 2008-01-16 | 1/16/2008 Meeting Minutes were approved.
2 |  | C | Post Final BPS/ESS/ITS 05/03/2007 meeting minutes | NAESB Staff | 2008-01-16 |  |  | Action item is dependent on the completion of Action Item 1.
3 |  | C | Approve BPS/ESS/ITS 06/01/2007 meeting minutes | Subcommittee |  |  | 2008-01-16 | 1/16/2008 Meeting Minutes were approved.
4 |  | C | Post Final BPS/ESS/ITS 06/01/2007 meeting minutes | NAESB Staff | 2008-01-16 |  |  | Action item is dependent on the completion of Action Item 3.
5 |  | C | Approve BPS/ESS/ITS 06/11/2007 meeting minutes | Subcommittee |  |  | 2008-01-16 | 1/16/2008 Meeting Minutes were approved.
6 |  | C | Post Final BPS/ESS/ITS 06/11/2007 meeting minutes | NAESB Staff | 2008-01-16 |  |  | Action item is dependent on the completion of Action Item 5.
7 |  | C | Approve BPS/ESS/ITS 06/22/2007 meeting minutes | Subcommittee |  |  | 2008-01-28 | 1/28/2008 Meeting Minutes were approved.
8 |  | C | Post Final BPS/ESS/ITS 06/22/2007 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 7.
9 |  | C | Approve BPS/ESS/ITS 07/06/2007 meeting minutes | Subcommittee |  |  | 2008-01-16 | 1/16/2008 Meeting Minutes were approved.
10 |  | C | Post Final BPS/ESS/ITS 07/06/2007 meeting minutes | NAESB Staff | 2008-01-16 |  |  | Action item is dependent on the completion of Action Item 9.
11 |  | C | Approve BPS/ESS/ITS 07/23/2007 and 07/24/2007 meeting minutes | Subcommittee |  |  | 2008-01-16 | 1/16/2008 Meeting Minutes were approved.
12 |  | C | Post Final BPS/ESS/ITS 07/23/2007 and 07/24/2007 meeting minutes | NAESB Staff | 2008-01-16 |  |  | Action item is dependent on the completion of Action Item 11.
13 |  | C | Approve BPS/ESS/ITS 08/16/2007 and 08/17/2007 meeting minutes | Subcommittee |  |  | 2008-01-16 | 1/16/2008 Meeting Minutes were approved.
14 |  | C | Post Final BPS/ESS/ITS 08/16/2007 and 08/17/2008 meeting minutes | NAESB Staff | 2008-01-16 |  |  | Action item is dependent on the completion of Action Item 13.
15 |  | C | Approve BPS/ESS/ITS 08/28/2007 meeting minutes | Subcommittee |  |  | 2008-01-16 | 1/16/2008 Meeting Minutes were approved.
16 |  | C | Post Final BPS/ESS/ITS 08/28/2007 meeting minutes | NAESB Staff | 2008-01-16 |  |  | Action item is dependent on the completion of Action Item 15.
17 |  | C | Approve BPS/ESS/ITS 09/11/2007 and 09/12/2007 meeting minutes | Subcommittee |  |  | 2008-01-16 | 1/16/2008 Meeting Minutes were approved.
18 |  | C | Post Final BPS/ESS/ITS 09/11/2007 and 09/12/2007 meeting minutes | NAESB Staff | 2008-01-16 |  |  | Action item is dependent on the completion of Action Item 17.
19 |  | C | Approve BPS/ESS/ITS 10/10/2007 meeting minutes | Subcommittee |  |  | 2008-01-16 | 1/16/2008 Meeting Minutes were approved.
20 |  | C | Post Final BPS/ESS/ITS 10/10/2007 meeting minutes | NAESB Staff | 2008-01-16 |  |  | Action item is dependent on the completion of Action Item 19.
21 |  | C | Approve BPS/ESS/ITS 10/25/2007 meeting minutes | Subcommittee |  |  | 2008-01-16 | 1/16/2008 Meeting Minutes were approved.
22 |  | C | Post Final BPS/ESS/ITS 10/25/2007 meeting minutes | NAESB Staff | 2008-01-16 |  |  | Action item is dependent on the completion of Action Item 21.
23 |  | C | Approve BPS/ESS/ITS 11/07/2007 meeting minutes | Subcommittee |  |  | 2008-03-10 | Minutes were approved on 3/12/2008.
24 |  | C | Post Final BPS/ESS/ITS 11/07/2007 meeting minutes | NAESB Staff |  |  |  | Completed
25 |  | C | Approve BPS/ESS/ITS 11/19/2007 meeting minutes | Subcommittee |  |  | 2008-03-10 | Minutes were approved on 3/12/2008.
26 |  | C | Post Final BPS/ESS/ITS 11/19/2007 meeting minutes | NAESB Staff |  |  |  | Completed
27 |  | C | Approve BPS/ESS/ITS 11/26/2007 meeting minutes | Subcommittee |  |  | 2008-01-28 | 1/28/2008 Meeting Minutes were approved.
28 |  | C | Post Final BPS/ESS/ITS 11/26/2007 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 27.
29 |  | C | Approve BPS/ESS/ITS 12/07/2007 meeting minutes | Subcommittee |  |  |  | Minutes were approved on 4/17/08
30 |  | C | Post Final BPS/ESS/ITS 12/07/2007 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 29. Meeting minutes were posted on 4/28/08.
31 |  | C | Approve BPS/ESS/ITS 12/10/2007 meeting minutes | Subcommittee |  |  |  | Minutes were approved on 4/17/08
32 |  | C | Post Final BPS/ESS/ITS 12/10/2007 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 31. Meeting minutes were posted on 4/28/08.
33 |  | C | Approve BPS/ESS/ITS 12/17/2007 meeting minutes | Subcommittee |  |  |  | Approved at May 1st meeting
34 |  | C | Post Final BPS/ESS/ITS 12/17/2007 meeting minutes | NAESB Staff |  |  |  | Final meeting minutes werer posted on May 2nd.
37 |  | C | Write-up on why no further action is needed for TRM in systemdata and TRMID | Barbara Rehman Chris Advena |  |  |  | 04/04 - Recommendation for TRM has been developed. This action item is no longer applicable.
38 |  | C | Post Barbara Rehman's write-up (why no further action is needed for TRM in systemdata and TRMID | NAESB Staff |  |  |  | 04/04 - Recommendation for TRM has been developed. This action item is no longer applicable.
39 |  | C | Cover letter for list of ATC information that will not be made publicly available | Barry Green | 2007-11-26 | 2007-12-03 |  | Provided
40 |  | C | Post document provided by Barry Green (cover letter for list of ATC information that will not be made publicly available) | NAESB Staff |  | 2007-12-03 | 2007-12-07 | Posted. Moved to Jan 16-17 meeting.
41 |  | C | Combine NERC Hand-off Lists | Marcie Otondo |  |  |  | Not provided. Anticipate will be provided in Feb, 2008. 2/8 - Review Session is scheduled for 2/11 with small group. 4/4 - Document sent to NAESB to post for April 7th Joint Conference Call with NERC.
42 |  | C | Post document provided by Marcie Otondo (NERC Hand-off Lists) | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 40. Document not yet provided. List sent to NAESB on 4/4 Document was posted for NERC/NAESB 4/7 Meeting
43 |  | C | Summary of Formal Comments on 1.6 and 1.7 standards | Marcie Otondo |  |  |  | Provided
44 |  | C | Post documents provided by Marcie Otondo (summary of formal comments on 1.6 and 1.7 standards) | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 43. Posted. Will be addressed at Jan 16-17 meeting.
45 |  | C | Revise Order 890 Work Plan to reflect numbering system proposed for 2008 Annual Plan | Marcie Otondo |  |  |  | Provided 1/10/2008
46 |  | C | Post document provided by Marcie Otondo (revised Order 890 Work Plan to reflect numbering system proposed for 2008 Annual Plan) | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 45. 2/9 - Co-chairs are revising work plan to include 890-A cites and updates. This Action Item has been superseded by Action Item 90.
47 |  | C | Standards Language for Annotations for Changes to TTC/ATC and for ATC of zero for 6 months | Allen Pritchard |  |  |  | Provided
48 |  | C | Post documents provided by Allen Pritchard (standards language for annotations for changes to TTC/ATC and for ATC of zero for 6 months) | NAESB Staff |  |  |  | Posted. On-going discussion of Standard to continue on 1/11/2008.
49 |  | C | Request associated with the Standards Language for Annotations for Changes to TTC/ATC and for ATC of zero for 6 months | Allen Pritchard |  |  |  | Provided
50 |  | C | Post documents provided by Allen Pritchard (request for standards language for annotations for changes to TTC/ATC and for ATC of zero for 6 months) | NAESB Staff |  |  |  | Posted. On-going discussion of Standard to continue on 1/11/2008.
51 |  | C | List of ATC Information that Will Not be Made Publicly Available | Barry Green |  |  |  | Provided
52 |  | C | Post document provided by Barry Green (list of ATC information that will not be made publicly available) | NAESB Staff |  |  |  | Posted. On 1/16/2008 - 1/17/2008 agenda.
53 |  | C | Draft Standards for Posting on OASIS of Acutal Daily Peak Load | Marilyn Franz |  |  |  | Provided
54 |  | C | Post document provided by Marilyn Franz (draft standards for posting on OASIS of acutal daily peak load) | NAESB Staff |  |  |  | Posted. On 1/16/2008 - 1/17/2008 agenda.
55 |  | C | Draft Request for Standards for Posting on OASIS of Acutal Daily Peak Load | JT Wood |  |  | 2008-02-13 | Draft recommendation/standards were developed on 1/11/2008 and revised on 1/31/2008.
56 |  | C | Post document provided by Marilyn Franz (draft request for standards for posting on OASIS of acutal daily peak load) | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 55. Note documents were developed by JT Wood.
61 |  | C | Draft Standards for Posting on OASIS Load Forecast / Assumptions | JT Wood |  |  |  | Due date moved until received responses from NERC on related questions. 2/9 - JT Wood provided draft of standards and recommendation on 1/11/2008 and revised document on 01/31/2008.
62 |  | C | Post document provided by Marilyn Franz (draft standards for posting on OASIS load forecast / assumptions | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 66.
63 |  | C | Draft Request for Standards for Posting on OASIS Load Forecast / Assumptions | JT Wood |  |  |  | Due date moved until received responses from NERC on related questions. Draft document was provided on 1/11/08 and revised on 1/31/08
64 |  | C | Post document provided by Marilyn Franz (draft request for standards for posting on OASIS load forecast / assumptions) | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 68. Document was posted for 2/13/2008 meeting
65 |  | C | Identify NAESB requirements in Order 890-A, include in the "matrix", determine wheter item is new, changed or unchanged | NAESB Staff | 2008-01-03 | 2008-01-11 |  | 1/15/08 - Listing of references to NAESB in Order 890-A were provided to co-chairs of BPS/ESS/ITS
66 |  | C | Post document provided by NAESB staff (revised matrix to include Order 890-A) | NAESB Staff | 2008-01-03 |  | 1/16-17/2008 | Action item is dependent on the completion of Action Item 65. 1/16/08 - Document was posted to BPS/ESS/ITS, ESS, and ITS web pages
67 |  | C | Determine appropriate subcommittee to address Order 890-A requirements | BPS/ESS/ITS Chairs | 2008-01-03 |  |  | Action item is dependent on the completion of Action Item 54. 1/25/08 - Subcommittee chairs reviewed document and identified those cites which should be included in the 890 work plan. The 890 work plan will be updated and changes will be proposed for the 2008 annual plan.
68 |  | C | Include chairs Order 890-A assignments in Order 890 Work Plan | Marcie Otondo | 2008-01-03 |  |  | Action item is dependent on the completion of Action Item 67.
69 |  | C | Forward to NERC questions on Load Forecast | NAESB Staff |  |  |  | 3/15 - The load forecast recommendation was voted out of subcommittee on 3/10. No further action is required on this item.
70 |  | C | Forward to NERC question on standard language for annotating the reason for changes to ATC/TTC | NAESB Staff |  |  |  | 2/16 - No longer applicable. On 2/13 the recommendation was voted out of subcommittee. No further work will be done by the subcommittee unless directed by the EC after the 30-day formal comment period.
71 |  | C | Forward to NERC the list of items not posted on OASIS and request which items should not be posted due to security and/or reliability concerns | NAESB Staff |  |  |  | List was provided to Andy Rodriguez on 1/18/2008 by Ed Skiba
72 |  | C | Cover Note for List of ATC Information that Will Not be Made Publicly Available | Barry Green |  |  | 2008-01-18 | Provided 1/18/2008 - Cover letter was reviewed and approved by the BPS/ESS/ITS to post for informal comments.
73 |  | C | Post document provided by Barry Green (Cover Note for List of ATC Information that Will Not be Made Publicly Available) | NAESB Staff |  |  | 2008-01-18 | Posted
74 |  | C | Examples appendix to complement the Standards for Annotations for Changes to TTC/ATC and for ATC of zero for 6 months |  |  |  |  | 02/16 - Action item has been superseded by action item # 96. No further action is required on this item.
75 |  | C | Post documents provided by ________ (Example appendix to complement the Standards for Annotations for Changes to TTC/ATC and for ATC of zero for 6 months) | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 74. 2/16 - Action item has been superseded by action item # 96. No further action is required on this item.
76 |  | C | Document explaining the 3 "levels" of posting changes to TTC/ATC narratives | P. Sorenson |  |  |  | Completed
77 |  | C | Post documents provided by P. Sorenson (3 levels of posting changes to TTC/ATC narratives) | NAESB Staff |  |  |  | Completed
79 |  | C | Review Postback list and provide update to BPS/ESS/ITS | Andy Rodriguez | 2008-02-08 |  | 2008-03-10 | Information was provided by Andy Rodriguez and posted for Phoenix Meetings
82 |  | C | Approve BPS/ESS/ITS 01/18/2008 meeting minutes | Subcommittee | 2008-01-18 |  | 2008-02-13
83 |  | C | Post Final BPS/ESS/ITS 01/18/2008 meeting minutes | NAESB Staff |  |  |  | Completed
84 |  | C | Post Publicly Available ATC Information Request for Informal Comments | NAESB Staff | 2008-01-18 |  |  | 1/22/08 - Document was posted for informal comments.
87 |  | C | Provide Postback list to Andy Rodriguez | Marcie Otondo | 2008-02-08 | 2008-02-08 | N/A | List was emailed to Andy Rodriguez.
88 |  | C | Provide NERC comments on ATC Information List | Andy Rodriguez | 2008-01-18 | 2008-02-22 |  | Feedback was provided to co-chairs and NAESB staff on 4/7/08
89 |  | C | Revise 890 work plan to include 890-A cites | Marcie Otondo Ed Skiba | 2008-01-25 | 2008-02-22 |  | Document was updated and needs to be sent to NAESB to post 2/26
90 |  | C | Post revised 890 Work Plan | NAESB Staff | 2008-02-09 | 2008-02-22 | 2008-03-10 | Action Item is dependent on Action Item 89. 3/5 - Document has been updated and is posted
91 |  | C | Provide Updates to 2008 Annual Plan to Kathy York, Rea McQuade | Ed Skiba, Marcie Otondo, JT Wood, Paul Sorenson | 2008-02-07 | 2008-02-22 |  | Updated document was sent to Rae McQuade, Kathy York and others on 2/28/2008.
92 |  | C | Update ATC/TTC Recommendation to include changes to WEQ 002, 003, and 013 | JT Wood | 2008-01-28 |  | 2008-02-13 | Updates were provided on 1/31/2008. Document has been posted for 2/13/2008 meeting
96 |  | C | Small team headed by Allan Pritchard to develop examples to be included in ATC/TTC Recommendation | Allan Pritchard, Barry Green, JT Wood, Narinder Saini, Ron Slagel | 2008-02-13 | 2008-02-21 | N/A | Examples are to be provided to NAESB staff to be included in Recommendation. Examples for Recommendation have been updated and are included in the ATC/TTC recommendation which was posted for the 30 day formal comment period on 2/29
97 |  | C | Rework Parking Lot and Motions lists so they are by recommendation | Ed Skiba | 2008-02-13 | 2008-02-15 |  | 2/15 - Documents have be reworked and posted on the Joint BPS & ESS/ITS web page.
98 |  | C | Clean-up ATC/TTC Narrative Recommendation prior to posting for 30-day formal comment period. | NAESB Staff | 2008-02-13 | 2008-02-22 | N/A | Action Item is dependent on completion of item 96. Document was updated and posted for 30-day formal comment period on 2/29/2008.
101 |  | C | Approve BPS/ESS/ITS 02/13/2008 meeting minutes | Subcommittee | 2008-02-13 |  |  | Closing this action item. It is a duplicate of Action Item 99.
102 |  | C | Post Final BPS/ESS/ITS 02/13/2008 meeting minutes | NAESB Staff |  |  |  | Closing this action item. It is a duplicate of Action Item 100.
105 |  | C | Approve BPS/ESS/ITS 02/27/2008 meeting minutes | Subcommittee | 2008-02-27 |  | 2008-03-10 | Minutes were approved on 3/12/2008.
106 |  | C | Post Final BPS/ESS/ITS 02/27/2008 meeting minutes | NAESB Staff |  |  |  | Final Meeting minutes were posted.
107 |  | C | Find and post draft document associated with MOD 003 prior to Phoenix meetings | JT Wood | 2008-02-27 | 2008-03-07 |  | Changes for MOD 003 were address through Recommendation 2008 AP Item 2.b.vii (WEQ-001 changes for “ATC Information Link” on OASIS and TTC and ATC methodologies and values). No further action is required on this Action Item.
108 |  | C | Update Load Forecast Recommendation and repost for Phoenix Meeting | JT Wood, Ed Skiba | 2008-02-27 | 2008-03-03 | 2008-03-10 | Updated recommendation was posted on 3/3/2008.
109 |  | C | Approve Backlog of Joint NERC ATCDT/NAESB BPS/ESS/ITS meeting minutes | Subcommittee, NERC ATCDT | 2008-02-29 | 2008-04-07 |  | Meeting Minutes approved on 4/7/08
110 |  | C | Post final meeting minutes of approved backlog of Joint NERC ATCDT/NAESB BPS/ESS/ITS meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 109. Backlog of meeting minutes were posted on 4/28/08.
111 |  | C | Develop detailed Agenda for BPS/ESS/ITS Meetings in Phoenix | Ed Skiba, JT Wood, Marcie Otondo, Paul Sorenson | 2008-02-27 | 2008-03-07 | 2008-03-06
112 |  | C | Approve Joint NERC/NAESB meeting minutes from March 5, 2008 Meeting | Subcommittee, NERC ATCDT | 2008-03-05 | 2008-04-07 |  | Minutes were approved on 4/7/08.
113 |  | C | Post Joint NERC/NAESB approved meeting minutes from March 5, 2008 Meeting | Subcommittee, NERC ATCDT | 2008-03-05 | 2008-04-07 |  | Action item is dependent on the completion of Action Item 112. Meeting minutes were posted on 4/28/08.
114 |  | C | Approve BPS/ESS/ITS 03/10/2008 - 03/13/2008 meeting minutes | Subcommittee | 2008-03-13 |  |  | Minutes were approved on 4/17/08.
115 |  | C | Post Final BPS/ESS/ITS 03/10/2008 - 03/13/2008 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 114. Meeting minutes were posted on 4/28/08.
116 |  | C | Clean-up of recommendation WEQ AP Item 2.b.v.2 and post for formal comments | NAESB Staff | 2008-03-13 | 2008-03-17 |  | Recommendation was posted for formal comments on 3/17
117 |  | C | Clean-up of recommendation WEQ AP Item 2.b.vii and post for formal comments | NAESB Staff | 2008-03-13 | 2008-03-17 |  | Recommendation was posted for formal comments on 3/17
118 |  | C | Draft Postback Standards Document | Don Williams to lead team | 2008-03-12 | 2008-03-24 | 2008-03-31 | Document was reviewed on 04/16 -04/17
119 |  | C | Draft Counterflow Standards | Don Williams to lead team | 2008-03-12 | 2008-04-09 | 2008-04-16 | Document was reviewed on 04/17
120 |  | C | Prepare document pulling 890 & 890-A Information on what needs to be address under AP Item 2.b.v.1 | Barbara Rehman | 2008-03-13 | 2008-04-04 | 2008-04-07 | Partial document was reviewed on March 28th. Final version of the document is to be provided for review at the April 7th Meeting. 04/07 - Joint Subcommittee reviewed the document and determined no further action was required on the document. All outstanding items have been captured on the concepts list.
121 |  | C | Develop tracking tool to determine what 890/890-A Annual Plan Items have been completed | Ed Skiba, JT Wood, Marcie Otondo, Paul Sorenson | 2008-03-13 |  | 2008-03-28 | Tracking tool was included in the NAESB Board Packet
122 |  | C | Develop Agenda for March 28 Conference Call | Ed Skiba, JT Wood, Marcie Otondo, Paul Sorenson | 2008-03-13 | 2008-03-20 |  | Agenda provided to J Booe on 3/17
123 |  | C | Develop Agenda for March 31 Conference Call | Ed Skiba, JT Wood, Marcie Otondo, Paul Sorenson | 2008-03-13 | 2008-03-24 |  | Agenda provided to J Booe on 3/17
124 |  | C | Develop Agenda for April 7 Conference Call | Ed Skiba, JT Wood, Marcie Otondo, Paul Sorenson | 2008-03-13 | 2008-04-02 |  | Agenda was posted on 4/2
125 |  | C | Update 890 Work Plan to reflect updates from 3/10-3/13 Meetings | Ed Skiba, JT Wood, Marcie Otondo, Paul Sorenson | 2008-03-13 | 2008-03-24 | 2008-03-28
127 |  | C | Send Andy Rodriquez list of ATC calculation frequency questions to be discussed during April 7th NERC/NAESB Conference Call | Ed Skiba | 2008-03-28 |  | 2008-04-07 | Document sent on 3/28. Revised document sent on 04/03.
128 |  | C | Begin drafting Recommendation for 2008 AP Item 2.b.v.1 Business Practices to address frequency and posting of all ATC Components | Ed Skiba | 2008-03-28 |  | 2008-04-17 | Recommendation was sent to NAESB staff on 4/23 for final clean-up to be posted for 30-day formal comment period.
129 |  | C | Post ESS/ITS and BPS 890 Progress report on http://www.naesb.org/weq/weq_atc_afc.asp webpage | NAESB Staff | 2008-03-28 |  |  | Revised progress report was sent to NAESB on 04/08/08. Documents were posted on 04/14/07.
130 |  | C | Compile TRM Background Document | Ed Skiba | 2008-03-28 |  | 2008-03-31 | 3/29 - Document was sent to Exploder list and to NAESB for posting
131 |  | C | Post ESS/ITS and BPS Action Items List on http://www.naesb.org/weq/weq_atc_afc.asp webpage | Ed Skiba NAESB Staff | 2008-03-28 |  |  | Revised list sent to NAESB on 04/08/08. Documents were posted on 04/14/07.
132 |  | C | Post final documents from March 31st meeting | Ed Skiba NAESB Staff | 2008-03-31 |  |  | Completed
133 |  | C | Draft TRM recommendation and post for 30 day formal comment period. Recommendation to state no additional NAESB Business Practices are required for WEQ AP 2.b.iv.1-3 | Co-Chairs NAESB Staff | 2008-03-31 |  |  | Document was posted for 30-day formal comment period on April 8th.
134 |  | C | Approve BPS/ESS/ITS 03/28/2008 meeting minutes | Subcommittee |  |  |  | Minutes were approved on 04/16
135 |  | C | Post Final BPS/ESS/ITS 03/28/2008 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 134. Meeting minutes were posted on 4/28/08.
136 |  | C | Approve BPS/ESS/ITS 03/31/2008 meeting minutes | Subcommittee |  |  |  | Minutes were approved on 04/16
137 |  | C | Post Final BPS/ESS/ITS 03/31/2008 meeting minutes | NAESB Staff |  |  |  | Action item is dependent on the completion of Action Item 136. Meeting minutes were posted on 4/28/08.
138 |  | C | Schedule next Joint NERC/NAESB meeting | Marcie Otondo Andy Rodriquez JT Wood Ed Skiba | 2008-04-07 |  |  | Conference call is scheduled from 9:00 - 11:00 CDT on May 1st, 2008.
139 |  | C | Review ATC follow-up items from NERC/NAESB meeting with BPS/ESS/ITS and incorporated in NAESB work scheduled | Marcie Otondo JT Wood Ed Skiba | 2008-04-07 | 2008-04-07 | 2008-04-07 | Items were reviewed and follow-up items were added to the ATC/AFC Concepts list.
144 |  | C | Develop and Post Agenda for April 16-17 Meeting | Co-Chairs NAESB Staff | 2008-04-07 | 2008-04-08 |  | Completed April 9th
146 |  | C | Co-chairs draft recommendation no additional standards need for Annual Plan Item 2.b.v.1 (ATC Components) | Ed Skiba | 2008-04-16 |  |  | Recommendation developed and reviewed by co-chairs and then submitted to NAESB on 04/23 for posting.
147 |  | C | NAESB Staff post recommendation no additional standards need for Annual Plan Item 2.b.v.1 (ATC Components) | NAESB Staff | 2008-04-16 |  |  | Document was posted for 30-day formal comment period on April 23rd.
148 |  | C | Revise Postback recommendation based on direction provided by Joint BPS/ESS/ITS Subcommitteed | JT Wood | 2008-04-17 | 2008-04-22 |  | Document sent to NAESB on 04/22.
149 |  | C | Post Postback recommendation for Informal Comments | NAESB Staff | 2008-04-17 | 2008-04-23 |  | Document was posted for informal comments on 4/23. Comments are due by May 7th
150 |  | C | Distribute the Midwest ISO Congestion Management Process approach for counterflows to list serve subcommittee exploder list | Ed Skiba, John Harmon | 2008-04-17 |  |  | Document sent to Joint BPS/ESS/ITS exploder list on 04/22
153 |  | C | Develop and Post Agenda for May 1st NERC/NAESB Meeting | Co-Chairs NAESB Staff | 2008-04-17 | 2008-04-25 |  | Agenda was posted on 4/28/08
154 |  | C | Develop and Post Agenda for May 1st BPS/ESS/ITS Meeting | Co-Chairs NAESB Staff | 2008-04-17 | 2008-04-25 |  | Agenda was posted on 4/25/08
155 |  | C | Create CBM Parking Lot to include issues/concerns raised by NERC | Ed Skiba | 2008-05-01 | 2008-05-02 |  | CBM Parking Lot was submitted to NAESB for posting
156 |  | C | Create no action required recommendation for WEQ Annual Plan Item 2.b.vi | Co-Chairs NAESB Staff | 2008-05-01 | 2008-05-05 |  | Recommendation has been posted for the 30-pday formal comment period.
157 |  | C | Verify with Andy Rodriquez that NERC has completed it review of the ATC Information List. | Ed Skiba | 2008-05-01 | 2008-05-02 |  | 5/2 - Confirmed with Andy that NERC was not planning on doing any additional reviews. However, if the Joint ESS/ITS and BPS has questions on the NERC response they can send questions to Andy to follow-up.