## Sheet1
WEQ ESS/ITS Progress Report Based on WEQ 2008 Annual Plan As of December 08, 2008
Annual Plan Item | Annual Plan Item | Scheduled | Underway | Concept Discussion | Draft Recommen- dation | Sub-committee Review | Post Informal Comments | Review Comments | Sub-committee Final Review | Sub-committee Approval | NAESB Clean-up | Post for Formal Comments | EC Passed | Ratified
2007AP 2.a.i | Resales
2.a.i.1 | Conditional Firm, Annotations For ATC; Load Forecast And Actual Load; Re-Bid Of Partial Service; And Preconfirmation Priority S&CP Requirements | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a.i.2 | Conditional Firm Business Practice Standards associated with S&CP Requirements completed in 2(a)(i)(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a.i.5 | Re-Bid Of Partial Service Business Practice Standards on a Single Transmission Provider’s System associated with S&CP Requirements completed in 2(a)(i)(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a.i.6 | Preconfirmation Priority Business Practice Standards associated with S&CP Requirements completed in 2(a)(i)(1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a.i.7 | OASIS Exemptions Appendix | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a.ii.1 | Metrics Related to Provision of Transmission Service (Paragraph 413 of Order 890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a.ii.2 | Metrics Related to Performance of Transmission Studies (Paragraphs 1308 through 1317 of Order 890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a.ii.3 | Redispatch Cost Posting | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.a.iii.1 | Use of OASIS to Make Electronic Requests to Designate and Terminate Network Resource | 0 | 0 | 0
2.a.iii.2 | Ability to Query Requests to Designate and Terminate Network Resources and Allow for Queries of All Information Provided with Designation Requests | 0 | 0 | 0
2.a.iii.3 | Masking of Designated Network Resource Operating Restrictions and Generating Cost Information | 0 | 0 | 0
2.a.iii.4 | Procedural Requirements for Submitting Designations over new OASIS Functionality | 0 | 0 | 0
2.a.iii.5 | Specify How Designated Network Service Informational Postings are Posted on OASIS | 0 | 0 | 0
2.a.iii.6 | Set Forth the Treatment of OASIS Requests when the Customer Fails to Provide the Necessary Attestation | 0 | 0 | 0
2.a.iii.7 | Procedural Requirements for Submitting Both Temporary and Indefinite Terminations of Network Resources | 0 | 0 | 0
2.a.iii.8 | Procedures for Submitting and Processing Requests for Concomitant Evaluations of Transmission Requests and Temporary Terminations | 0 | 0 | 0
2.a.iv.1 | Pre-Emption | 0
2.a.iv.2 | Request No. R05019 | 0
2.a.iv.3 | Revisions to Standard 9.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 9.7 assigned to ec task force
2.a.v.1 | Paragraph 1377 | 0
2.a.v.2 | Re-Bid Of Partial Service across Multiple Transmission Providers’ Systems | 0
2.a.vi.1 | Paragraph 1390 of Order 890 | 0
2.a.vi.2 | Paragraphs 1627 of Order 890 | 0
2.a.vi.3 | Redispatch Cost Posting to allow for posting of third party offers of planning redispatch services. | 0
2.a.vi.4 | Posting of Existing Transmission Commitments (ETC) (moved from Group 1) | 0
2.a.vii.1 | Tagging for Conditional Firm Service | 0
2.b.i.1 | The processing of transmission service requests, which use TTC/ATC/AFC, in coordination with NERC changes to MOD 001 | 0
3.a.i | Develop OASIS S&CP changes to support OASIS business practices. | 0 | [11 empty] | no ratification needed
3.a.ii | Network Services: Determine and develop needed business practice standards or other support is needed to support use of OASIS for Network Service transactions (R04006E). (Related to AP 2(a)(iii)) | 0
3.a.v | Document procedures used to implement the displacement/interruption terms of the Pro Forma tariff (R05019). | 0
3.a.vi.2 | Eliminate Masking of TSR tag source and sink when requested status is denied, withdrawn refused, displaced, invalid, declined, annulled or retracted | 0
3.a.vi.3 | Initiate standard that requires ALL historical transmission service reservations to be available for review up to a number of years in the past. | 0 | [11 empty] | no ratification needed
3.a.vi.4 | Initiate standard that eliminates the disparity of posting "sensitive" information. This standard should also include procedures of user certification that allows access to this class of information. | 0
3.a.vi.5 | Enhance the TSR result postings to allow showing of (i) limiting transmission elements and (ii) available generation dispatch options that would allow acceptance of reservation request. | 0
3.a.vi.6 | Standardize the availability of TSR study result postings, eliminating practice of some Transmission Owners that charge for viewing these documents. | 0
3.a.vii | Respond to issues in FERC Order No. 676 (Docket No. RM05-5-000) – NAESB WEQ Standards 001 9.7, (paragraph 51 of the order). | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 9.7 assigned to ec task force
3.b.ii | Develop PKI standards for OASIS. | 0
6.c.1 | OASIS Consistency Changes (R08001, R08002, R08003, R08005) | 0
6.e.i | Modify NAESB definitions related to OASIS Business Practices (001, 002, 003, and 013) | 0 |  | reassigned to subcommittee co-chairs
6.h | Develop standards to allow for registered Market Operators to request changes to the Market Level profile of Implemented Interchange (R06006) | 0 |  |  | reassigned to JISWG
6.j | Develop a standard mechanism to implement a “RECALL” of transmission capacity from an existing confirmed transmission service reservation/Specify the technical requirements for implementation of a new OASIS request type, RECALL. (R07001) | 0 | [11 empty] | no ratification needed
6.k | Clarify the S&CP implementation of the DEFERRAL request. (R07003) | 0 | [11 empty] | no ratification needed
6.l | Develop business practice and technical standards for assigning, tracking, and limiting rollover rights. (R07004) | 0 | [11 empty] | ratification needed
6.n | Consistent with ¶51 of FERC Order No. 890-A, add AFC and TFC values to the “System_Attribute” data element of the NAESB Standard WEQ-003: OASIS S&CP Data Dictionaries. (R08011) | 0
provisional 5 | Develop business practices for allocating capacity among requests received during a submittal window Order 890-A (Docket Nos. RM05-17-001, 002 and RM05-25-001, 002 - Paragraph 805) | 0
LEGEND:
Completed Prior to November 2008 EC Meeting
Completed since November 2008 EC Meeting
890 Work Plan
Normal Annual Plan Items
New Items Added
AP items linked together
AP items linked to 9.7
AP items linked to nits
AP items linked to 5019
AP items linked to services across multiple TP
AP items linked to conditional firm
AP items linked to metrics/rebid